“ISSUES AND OPTIONS

FOR CTI PLAN OF ACTION”

DECISION DRAFT FOR

MARINE PROTECTED AREAS (MPAs) ESTABLISHED AND EFFECTIVELY MANAGED

CORAL TRIANGLE INITIATIVE (CTI)

ON CORAL REEFS, FISHERIES AND FOOD SECURITY

A technical background document prepared by the CTI Regional Secretariat

to help inform the development of the CTI Plan of Action

(Draft #1; May 14, 2008)

- This technical background document, prepared by the Regional CTI Secretariat, is designed to help inform the governmental discussions on the contents of the CTI Plan of Action. In particular, it is being provided at this time to support preparations for the first meeting of the CTI Coordination Committee. The document focuses on the five over-arching goals of the Plan of Action that were agreed at the first Senior Officials Meeting (SOM1): priority seascapes; ecosystem approach to managing fisheries; marine protected areas; climate change adaptation; and threatened species status. For each goal, key issues are summarized, and options for possible objectives and high-level strategies are presented for consideration. This document is designed to serve as a useful starting point for in-depth discussions by the six Coral Triangle governments on the contents of the Plan of Action. The information is structured to help facilitate a systematic approach to building a consensus around the important and complex issues that will be addressed in the Plan of Action.

- OPTIONS FOR CTI PLAN OF ACTION

Based on the background information and key issues analysis, CT governments may wish to consider the following options for inclusion in the CTI Plan of Action.

Objective #1. Coral Triangle Heritage Sites System of marine protected areas.  By 2020, a comprehensive, ecologically representative, fully functioning, and region-wide Coral Triangle Heritage Sites System of marine protected areas will be in place—covering at least 20% of the critical marine and coastal habitats across the Coral Triangle and designed in ways that significantly improve the income, livelihoods and food security of coastal communities, and conserve the region’s rich biological diversity.

Annotations to Objective #1:

- By 2015, through joint collaboration, our six governments will have in place a fully functioning, region-wide system of Coral Triangle Heritage Sites—representing a subset of total MPAs, and designed to protect the most critical marine and coastal biological resources across the CT.

- To be fully functional, the CT Heritage Sites System (CTHS) will be: (i) addressing critical needs of coastal communities (e.g., fisheries-related food security, risk reduction from natural disasters, sustainable livelihoods built around marine resources); (ii) ecologically representative, (iii) sustainably financed, (iv) resilient to climate change and other impacts, and (v) effectively managed.

- As a key innovation, the CTHS System will not be composed of isolated MPAs, but rather include, as a central feature, ecologically connected “networks” of MPAs. In addition, the System will include MPAs within the EEZ of individual countries, as well as trans-boundary MPAs.

- As general guidelines: (i) most sites within the CTHS System would include resource utilization zones as well as appropriately sized no-take replenishment zones required for replenishing / sustaining marine resources; and (ii) most sites would include no-take replenishment zones covering at least 30% of the MPA (as recommended in recent studies), although always taking into account local conditions.

Possible high-level strategies

- Strategy #1:  Establish overall goals, objectives and operational design elements for a CT Heritage Sites System.  By 2010, our six governments will jointly agree on overall goals, objectives, designation processes, coordination mechanisms, and other operational design aspects of a region-wide CTHS System, drawing on the most relevant existing processes and Networks (e.g., SSME tri-partite agreement, World Heritage Sites Network and ASEAN Heritage Sites Network, UNESCO Man and Biosphere Reserve Network).

- Strategy #2:  Complete and endorse the first iteration of a comprehensive map of the CT Heritage Sites System.  By 2011, our six governments will jointly complete and endorse a map delineating a region-wide CT Heritage Sites System, based on (i) extensive biophysical and socio-economic data analysis and geographic prioritization, (ii) science-based requirements for sustainable management of marine and coastal resources, and (iii) extensive in-country consultation processes. Special collaboration and external assistance from leading institutions will be required to analyze key issues not addressed in previous mapping exercises, such as spatial mapping of (i) fisheries-based food-security data; and (ii) poverty data overlaid with data on climate change vulnerability of marine ecosystems. Such data sets/maps would be used to help identify candidate MPA sites & networks.

- Strategy #3.  Establish an MPA Innovations Program and associated MPA Innovations Learning Network.  By 2010, each of our six governments will designate a small set of “MPA Innovation Sites and Programs” in our countries representing innovations being piloted for broader replication. Examples of such innovations could include: new approaches to co-management; “MPA campaigns” to raise local community awareness; local community benefit-sharing models; effective enforcement models (e.g., community self-enforcement, arrest/prosecution protocols); models in which MPAs serve as economic engines for local economies; self-financed MPA sites; and programs to scale up sustainable livelihoods around MPAs. By 2010, our six governments will jointly establish and put into operation an “MPA Innovations Learning Network” that proactively shares information and connects practitioners. Learning networks will operate at national and regional levels, and focus primarily on meeting practical, on-site needs.

- Strategy #4:  Help establish and operationalize a regional Coral Triangle Partnership Fund (CTPF), complemented by domestic funding mechanisms.  By 2012, our six governments—in collaboration with multiple donors and other partners—will jointly help establish and put into operation a large-scale region-wide CTPF, with highly streamlined operations and world-class standards built into its design. As a preliminary target, the CTPF should, over time, provide 50% of the recurrent annual costs to effectively manage the region-wide CTHS System—potentially drawing on both sinking and permanent endowment funds, as well as “revolving” funds (periodic replenishment of part of CTPF). A window within the CTPF, or perhaps a sister fund, could emphasize sustainable livelihoods and food security programs for coastal communities, directly linked to MPA management. Each of our six governments will provide an agreed level of “domestic funding” as co-financing to complement this international funding, based on country-specific capacities. Such domestic funding will include, for example, national budget allocations and tourism-based fee systems.

- Strategy #5:  Establish a special Forum for the Tourism and Travel Industry.  Given the direct benefits that flow to the tourism and travel industry from MPAs, a special forum of major companies in this industry will be established by 2012, focused on mobilizing new private sector financial support for MPAs, as well as best practices.

- Strategy #6:  Establish, strengthen and operationalize Capacity-leap Programs.  By 2012, in collaboration with partners and building on existing institutions, our six governments will jointly and individually establish, strengthen and put into operation a set of long-term capacity building programs and institutions. These will be designed to achieve a dramatic leap forward, in the coming decade, in the capacity to manage marine and coastal resources in the CT. Such programs and institutions will be designed to have long-term viability and impacts on broad geographical scales, servicing both government and non-governmental actors, with a primary focus on meeting practical, field-level management needs. One option to be explored would be the need for some type of Coral Triangle Center for Marine Protected Areas, providing regional services such as targeted training programs and technical assistance to a range of capacity-building institutions and individuals across the region.

- Strategy #7:  Achieve sustainable financing for all CT Heritage Sites.  By 2020, each of our governments will take the necessary actions to ensure that all of the CT Heritage Sites within our countries have full financing in place, drawing on a diversity of funding sources and strategies (e.g., Strategies #4 and #5 above, national budget allocations, trust funds, etc.).

- Strategy #8:  Track progress and achieve effective management across the entire CT Heritage Sites System.  By 2012, our six governments will jointly adopt & operationalize a well-defined monitoring program to assess management effectiveness over time of CT Heritage Sites / networks, drawing on active participation of scientific and research institutions and the many existing methodologies. By 2015, 50% of the CT Heritage Sites within each country and across the entire System will meet minimum management effectiveness standards.

- DECISION TO BE TAKEN

After thoroughly examining the issues, national, regional, and international initiatives and commitment for marine protected areas, all six government take the decision to:

- Accept (either as is, or with revisions that you think are needed)

- Requires further analysis and consideration (with suggestions for specific analysis needed)

- Reject (with explanations summarizing the basis of your objection)

- New idea (new Objectives or new High-level Strategies under existing objectives; these could be written up and circulated at the upcoming CTI Coordination Committee meeting)

Note: To help prepare for the discussions at the upcoming first meeting of the CTI Coordination Committee, each objective and each high-level strategy described above, or new ideas, could be assigned one of above categories by your government.

MPA networks refer to ecologically connected clusters of MPAs with a self-replenishing function. For example, MPAs that are resilient to climate change and other types of threats (having strong recruitment of coral larvae, fish and other organisms) can serve as “sources” that promote the recovery of damaged or depleted MPAs (“sinks”) in other parts of the network. As another example, MPAs within a specific network can meet the needs of various life-stages of highly migratory species.